## Large Generator & Load Requests
Last Updated: | 2025-04-08 |  |  | Interconnection Request List
Position | Active Project | Date Interconnection Request Received | Location | Interconnect Point | Type of Interconnection Service Requested | Requested In-Service Date | Projected In-Service Date | Line | Facility Type | Summer Output (MW) | Winter Output (MW) | Status | Comments
1 | No | 2018-08-15 | Douglas County, WA | Rocky Reach 230 KV Switchyard | Energy Resource | 2023-10-31 | 2023-10-31 | N/A | Solar | 250 | 250 | Withdrawn
2 | Yes | 2021-08-13 | Chelan County, WA | 115 KV T-Line | Transmission Line | 2023-04-01 | 2025-06-11 | 115KV | Load | 288 | 288 | LLIA Complete | Construction
3 | No | 2022-07-18 | Chelan County, WA | 115 KV T-Line | Transmission Line | 2023-07-01 | 2023-07-01 | 115KV | Load | N/A | N/A | Withdrawn
4 | No | 2022-11-25 | Douglas County, WA | Rocky Reach 230 KV Switchyard | Network Resource | 2025-12-31 | 2025-12-31 | N/A | Solar | 200 | 200 | Withdrawn
5 | No | 2023-01-30 | Chelan County, WA | 230 KV T-Line | Transmission Line | 2026-02-01 | 2027-02-01 | 230KV | Load | N/A | N/A | Withdrawn
6 | Yes | 2023-10-26 | Chelan County, WA | TBD | Energy Resource | 2027-12-31 | 2027-12-31 | TBD | Alternative | 100 | 100 | Facility Study
7 | No | 2023-10-26 | Chelan County, WA | 115KV T-Line | Transmission Line | 2024-08-01 | 2027-12-31 | 115KV | Load | 100 | 100 | Withdrawn
8 | No | 2023-11-14 | Chelan County, WA | 230KV T-Line | Transmission Line | 2029-12-31 | 2029-12-31 | 230KV | Load | 420 | 420 | Withdrawn
9 | No | 2023-11-14 | Chelan County, WA | 230KV T-Line | Transmission Line | 2029-12-31 | 2029-12-31 | 230KV | Load | 240 | 240 | Withdrawn
10 | Yes | 2024-02-16 | Chelan County, WA | 230KV T-Line | Transmission Line | 2027-02-16 | 2027-02-16 | 230KV | Load | 200 | 200 | System Impact Study
11 | Yes | 2024-03-25 | Chelan County, WA | 230KV T-Line | Transmission Line | 2024-09-30 | 2028-12-31 | 230KV | Load | 480 | 480 | Feasibility
12 | Yes | 2025-03-27 | Chelan County, WA | 230KV T-Line | Transmission Line | 2026-08-15 | 2026-08-15 | 230KV | Load | 460 | 450 | Feasibility