## Disclaimer
Disclaimer of completeness and accuracy of data provided to evaluate slice product
The information contained in this spreadsheet or report was queried from a database. Chelan PUD disclaims any warranty or representation that this information is completely accurate. Individual entries in the database may contain inaccuracies that could be reflected in this information. If you have any questions, please call Janet Jaspers: janet.jaspers@chelanpud.org or Mike Bradshaw: mike.bradshaw@chelanpud.org

## RR 2023-2028
Rocky Reach: planned outages 2023-2028 (as of 1/31/2023)
Tentative planned outages of 2 weeks or longer
Powerhouse | Unit | Work Description | Start | End | MW
ROCKY REACH | C01 | C01 2024 Overhaul | 2024-09-02 | 2024-10-11 | 105
ROCKY REACH | C02 | C02 2025 Overhaul | 2025-09-08 | 2025-10-24 | 105
ROCKY REACH | C03 | C03 2026 Overhaul | 2026-09-08 | 2026-10-09 | 105
ROCKY REACH | C04 | C04 2027 Overhaul | 2027-03-08 | 2027-04-23 | 105
ROCKY REACH | C05 | C05 2021 OVERHAUL/Governor control upgrades/Turbine hub refurbishment | 2022-03-24 | 2023-03-08 | 105
ROCKY REACH | C05 | Overhaul | 2027-09-13 | 2027-10-29 | 105
ROCKY REACH | C06 | C06 2026 Overhaul | 2026-03-23 | 2026-05-01 | 105
ROCKY REACH | C07 | C07 2024 Overhaul/Thrust Coolers/ Gen Breaker CCG | 2024-02-05 | 2024-03-15 | 105
ROCKY REACH | C08 | Complete overhaul and warranty inspection from 2022 outage that was shortened due to C11 disassembly | 2023-07-10 | 2023-09-08 | 130
ROCKY REACH | C08 | C08 2027 Overhaul | 2027-02-01 | 2027-03-12 | 130
ROCKY REACH | C09 | C09 2024 Overhaul/Turbine hub warranty inspection | 2024-03-25 | 2024-05-03 | 130
ROCKY REACH | C09 | C09 2028 Overhaul | 2028-09-11 | 2028-10-20 | 130
ROCKY REACH | C10 | Issue with shift ring | 2023-01-05 | 2023-01-20 | 130
ROCKY REACH | C10 | C10 Turbine rehab, governor upgrade | 2023-10-02 | 2024-12-06 | 130
ROCKY REACH | C10 | C10 2027 Overhaul/turbine hub warranty inspection | 2028-03-06 | 2028-04-21 | 130
ROCKY REACH | C11 | C11 will be in mothball status until turbine rehab outage begins in 2023 | 2022-11-01 | 2023-01-23 | 130
ROCKY REACH | C11 | C11 2020 TURBINE REPAIR- OH-GOVERNOR CONTROLS-EXCITER, AVR, BENTLY NEVADA | 2023-01-23 | 2024-03-23 | 130
ROCKY REACH | C11 | C11 2027 Overhaul/Turbine hub Warranty Inspection | 2028-09-11 | 2028-10-27 | 130

## RI 2023-2028
Rock Island Powerhouse 1: planned outages 2023-2028 (as of 1/31/2023)
Tentative planned outages of 2 weeks or longer
Powerhouse | Unit | Work Description | Start | End | MW
ROCK ISLAND #1 | B01 | 2016-2019 OUTAGE PRIOR TO MODERNIZATION | 2016-04-08 | 2025-03-25 | 17
ROCK ISLAND #1 | B01 | B01 2025-26 MODERNIZATION | 2025-03-25 | 2026-08-07 | 17
ROCK ISLAND #1 | B01 | End of Trial Operation | 2026-11-02 | 2027-01-01 | 17
ROCK ISLAND #1 | B01 | B01 2029 WARRANTY INSPECTION/OVHL | 2029-07-30 | 2029-10-05 | 17
ROCK ISLAND #1 | B02 | 2015-2019 OUTAGE PRIOR TO MODERNIZATION | 2016-01-19 | 2023-11-27 | 17
ROCK ISLAND #1 | B02 | B02 2023 MODERNIZATION | 2023-11-27 | 2025-04-11 | 17
ROCK ISLAND #1 | B02 | B02 Trial Inspection | 2025-07-07 | 2025-09-12 | 17
ROCK ISLAND #1 | B02 | B02 2028 WARRANTY INSPECTION | 2028-03-20 | 2028-06-02 | 17
ROCK ISLAND #1 | B03 | Turbine replacement | 2022-04-18 | 2023-12-16 | 17
ROCK ISLAND #1 | B03 | B03 Trial Operation Inspection | 2024-03-11 | 2024-05-14 | 17
ROCK ISLAND #1 | B03 | B03 2026 WARRANTY INSPECTION and OVHL | 2026-11-30 | 2027-02-05 | 17
ROCK ISLAND #1 | B04 | B04 2024 WARRANTY INSPECTION/OVHL | 2024-08-05 | 2024-10-11 | 17
ROCK ISLAND #1 | B05 | B05 2024 WARRANTY INSPECTION & OVH | 2024-02-19 | 2024-03-30 | 19
ROCK ISLAND #1 | B05 | B05 2030 OVERHAUL | 2028-09-11 | 2028-10-28 | 19
ROCK ISLAND #1 | B06 | B06 Trunnion seal and Hub design modifications | 2022-12-12 | 2023-08-14 | 19
ROCK ISLAND #1 | B06 | B06 End of Trial Operation Inspection | 2023-10-30 | 2023-12-29 | 19
ROCK ISLAND #1 | B06 | 2026 B06 Warranty Inspection/Overhaul | 2025-12-15 | 2026-02-25 | 19
ROCK ISLAND #1 | B07 | B07 2021 WARRANTY INSPECTION (Sunset date Feb 19 2023) | 2023-04-10 | 2023-05-19 | 19
ROCK ISLAND #1 | B07 | B07 2029 OVERHAUL | 2028-03-06 | 2028-04-22 | 19
ROCK ISLAND #1 | B08 | B08 2021 STATOR REPL TURBINE REHAB | 2024-02-12 | 2026-02-26 | 19
ROCK ISLAND #1 | B08 | B08 2026End of Trial Inspection | 2026-05-25 | 2026-07-24 | 19
ROCK ISLAND #1 | B08 | B08 2028 WARRANTY INSPECTION/Overhaul | 2028-07-17 | 2028-09-22 | 19
ROCK ISLAND #1 | B09 | B09 2022 Trunnion seal and Hub design modifications & OVHL | 2023-08-07 | 2024-04-05 | 19
ROCK ISLAND #1 | B09 | B09 End of Trial Operation Inspection | 2024-07-08 | 2024-09-05 | 19
ROCK ISLAND #1 | B09 | 2026 B09 Warranty Inspection/Overhaul | 2026-08-24 | 2026-11-04 | 19
ROCK ISLAND #1 | B10 | B10 2023 WARRANTY INSPECTION/OVHL | 2023-06-19 | 2023-08-25 | 19
ROCK ISLAND #1 | B10 | B10 2023 OVERHAUL | 2026-09-07 | 2026-10-24 | 19
Rock Island Powerhouse 2: planned outages 2023-2028 (as of 1/31/2023)
Tentative planned outages of 2 weeks or longer
Powerhouse | Unit | Work Description | Start | End | MW
ROCK ISLAND #2 | U01 | 2027 OVH | 2027-09-12 | 2027-11-12 | 42
ROCK ISLAND #2 | U02 | U02 2026 OVERHAUL | 2026-09-14 | 2026-11-19 | 42
ROCK ISLAND #2 | U03 | U03 2023 OVERHAUL | 2023-09-11 | 2023-11-22 | 42
ROCK ISLAND #2 | U03 | U03 2025 REHAB | 2025-06-09 | 2026-06-04 | 42
ROCK ISLAND #2 | U04 | 2024 OVH | 2024-09-10 | 2024-11-15 | 42
ROCK ISLAND #2 | U04 | U04 2025 REHAB | 2026-05-11 | 2027-05-07 | 42
ROCK ISLAND #2 | U05 | U05 2023 REHAB GOV HYDR, BRKR, MCCs & OVH | 2023-01-30 | 2024-06-01 | 42
ROCK ISLAND #2 | U05 | U05 2028 OVERHAUL | 2028-03-01 | 2028-05-11 | 42
ROCK ISLAND #2 | U06 | U06 2025 OVERHAUL | 2025-09-08 | 2025-11-12 | 42
ROCK ISLAND #2 | U06 | U06 2027 REHAB | 2028-03-13 | 2029-03-08 | 42
ROCK ISLAND #2 | U07 | U07 2024 REHAB | 2024-06-03 | 2025-06-27 | 42
ROCK ISLAND #2 | U08 | U08 2023 OVERHAUL | 2023-03-21 | 2023-05-25 | 42
ROCK ISLAND #2 | U08 | U08 2026 REHAB | 2027-04-19 | 2028-04-14 | 42