## Disclaimer
Disclaimer of completeness and accuracy of data provided to evaluate slice product
The information contained in this spreadsheet or report was queried from a database. Chelan PUD disclaims any warranty or representation that this information is completely accurate. Individual entries in the database may contain inaccuracies that could be reflected in this information. If you have any questions, please call Janet Jaspers: janet.jaspers@chelanpud.org or Mike Bradshaw: mike.bradshaw@chelanpud.org

## RR 2023-2028
Rocky Reach: planned outages 2024-2029 (as of 5/06/2024)
Tentative planned outages of 2 weeks or longer
Powerhouse | Unit | Work Description | Start | End | MW
ROCKY REACH | C11 | C11 2020 TURBINE REPAIR- OH-GOVERNOR CONTROLS-EXCITER, AVR, BENTLY NEVADA | 2023-01-23 03:10 | 2025-02-26 16:00 | 125.4
ROCKY REACH | C10 | C10 Turbine rehab, governor upgrade | 2023-10-02 07:00 | 2025-07-29 16:00 | 125.4
ROCKY REACH | C09 | Repair C-9 shift ring shims | 2024-02-15 07:00 | 2024-02-29 16:47 | 125.4
ROCKY REACH | C08 | C8 unit monitoring and controls upgrades | 2024-03-18 07:00 | 2024-04-04 12:29 | 125.4
ROCKY REACH | C09 | C09 2024 Overhaul/Turbine hub warranty inspection | 2025-03-10 06:10 | 2025-04-18 16:00 | 125.4
ROCKY REACH | C05 | C5 wicket gate bushings and servomotor piston replacement | 2025-04-21 05:00 | 2026-01-23 16:00 | 114
ROCKY REACH | C01 | C01 2024 Overhaul | 2025-09-08 06:10 | 2025-10-17 16:00 | 114
ROCKY REACH | C07 | C07 2024 Overhaul/Thrust Coolers/ Gen Breaker CCG | 2025-11-17 06:10 | 2025-12-29 16:00 | 114
ROCKY REACH | C02 | C02 2025 Overhaul | 2026-01-19 07:10 | 2026-03-06 16:00 | 114
ROCKY REACH | C06 | C06 2026 Overhaul | 2026-03-23 06:10 | 2026-05-01 17:50 | 114
ROCKY REACH | C03 | C03 2026 Overhaul | 2026-09-08 03:10 | 2026-10-09 17:50 | 114
ROCKY REACH | C08 | C08 2027 Overhaul | 2027-02-01 03:10 | 2027-03-12 17:50 | 125.4
ROCKY REACH | C04 | C04 2027 Overhaul | 2027-03-08 07:10 | 2027-04-23 16:00 | 114
ROCKY REACH | C05 | Overhaul | 2027-09-13 07:00 | 2027-10-29 16:00 | 114
ROCKY REACH | C10 | C10 2027 Overhaul/turbine hub warranty inspection | 2028-03-06 03:10 | 2028-04-21 16:00 | 125.4
ROCKY REACH | C09 | C09 2028 Overhaul | 2028-09-11 03:10 | 2028-10-20 19:50 | 125.4
ROCKY REACH | C11 | C11 2027 Overhaul/Turbine hub Warranty Inspection | 2028-09-11 06:10 | 2028-10-27 16:00 | 125.4
ROCKY REACH | C07 | C07 2029 OVERHAUL | 2029-01-22 07:10 | 2029-03-09 17:50 | 114
ROCKY REACH | C01 | C01 2029 Overhaul | 2029-09-10 03:10 | 2029-10-19 19:50 | 114

## RI 2023-2028
Rock Island Powerhouse 1: planned outages 2024-2029 (as of 5/06/2024)
Tentative planned outages of 2 weeks or longer
Powerhouse | Unit | Work Description | Start | End | MW
ROCK ISLAND #1 | B02 | 2015-2019 OUTAGE PRIOR TO MODERNIZATION | 2016-01-19 05:51 | 2024-08-09 06:00 | 20.7
ROCK ISLAND #1 | B01 | 2016-2019 OUTAGE PRIOR TO MODERNIZATION | 2016-04-08 15:51 | 2026-06-12 06:00 | 20.7
ROCK ISLAND #1 | B03 | Turbine replacement | 2022-04-18 06:50 | 2024-08-08 16:00 | 20.7
ROCK ISLAND #1 | B06 | B06 Trunnion seal and Hub design modifications | 2022-12-12 06:00 | 2024-01-24 15:35 | 22.5
ROCK ISLAND #1 | B09 | B09 2022 (2024) Trunnion seal and Hub design modifications & OVHL | 2024-02-05 07:00 | 2025-03-05 16:00 | 22.5
ROCK ISLAND #1 | B01 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 20.7
ROCK ISLAND #1 | B02 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 20.7
ROCK ISLAND #1 | B03 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 20.7
ROCK ISLAND #1 | B04 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 20.7
ROCK ISLAND #1 | B05 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 22.5
ROCK ISLAND #1 | B06 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 22.5
ROCK ISLAND #1 | B07 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 22.5
ROCK ISLAND #1 | B08 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 22.5
ROCK ISLAND #1 | B09 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 22.5
ROCK ISLAND #1 | B10 | Sweeny requesting 115 MW max output for PH1 due to work being performed on 6-950 | 2024-07-15 07:00 | 2024-08-04 16:00 | 22.5
ROCK ISLAND #1 | B02 | B02 2023 MODERNIZATION | 2024-08-09 07:00 | 2026-06-11 16:00 | 20.7
ROCK ISLAND #1 | B08 | B08 2021 (2025) STATOR REPL TURBINE REHAB | 2025-03-06 07:00 | 2026-12-20 16:00 | 22.5
ROCK ISLAND #1 | B01 | B01 2025-26 MODERNIZATION | 2026-06-12 07:00 | 2028-03-29 16:00 | 20.7
ROCK ISLAND #1 | B10 | B10 2023 OVERHAUL | 2026-09-07 07:10 | 2026-10-24 17:50 | 22.5
ROCK ISLAND #1 | B07 | B07 2029 OVERHAUL | 2028-03-06 07:10 | 2028-04-22 17:50 | 22.5
ROCK ISLAND #1 | B05 | B05 2030 OVERHAUL | 2028-09-11 07:10 | 2028-10-28 17:50 | 22.5
ROCK ISLAND #1 | B03 | overhaul | 2029-03-05 07:10 | 2029-04-21 17:50 | 20.7
ROCK ISLAND #1 | B04 | B04 2028 OVERHAUL | 2029-10-01 07:10 | 2029-11-21 17:50 | 20.7
Rock Island Powerhouse 2: planned outages 2024-2029 (as of 5/06/2024)
Tentative planned outages of 2 weeks or longer
Powerhouse | Unit | Work Description | Start | End | MW
ROCK ISLAND #2 | U05 | U05 2023 REHAB GOV HYDR, BRKR, MCCs & OVH | 2023-01-30 07:02 | 2024-10-25 16:00 | 51.3
ROCK ISLAND #2 | U06 | Inspect exciter cabinet for source of intermittent rotor ground | 2024-01-03 09:00 | 2024-01-18 17:12 | 51.3
ROCK ISLAND #2 | U02 | Required out for U04 draft tube gate cylinder and HPU refurbishment | 2024-03-18 07:00 | 2024-04-05 12:35 | 51.3
ROCK ISLAND #2 | U04 | 2024 OVH | 2024-03-18 07:00 | 2024-05-23 16:00 | 51.3
ROCK ISLAND #2 | U03 | Required out for U03 &U04 draft tube gate cylinder and HPU refurbishment | 2024-03-18 07:00 | 2024-04-19 10:37 | 51.3
ROCK ISLAND #2 | U01 | Required out for U01 Gen-lead replacement & U04 draft tube gate cylinder and HPU refurbishment | 2024-03-18 07:00 | 2024-04-12 20:06 | 51.3
ROCK ISLAND #2 | U01 | Exciter Field Lead Failure | 2024-04-23 07:05 | 2024-05-22 23:59 | 51.3
ROCK ISLAND #2 | U08 | Required out for U08 Gen-lead replacement & U07 draft tube gate cylinder and HPU refurbishment | 2024-09-16 07:00 | 2024-10-11 16:00 | 51.3
ROCK ISLAND #2 | U07 | Draft tube gate cylinder and HPU refurbishment | 2024-09-16 07:00 | 2024-10-18 16:00 | 51.3
ROCK ISLAND #2 | U07 | U07 2024 REHAB | 2024-10-31 07:00 | 2025-12-20 17:00 | 51.3
ROCK ISLAND #2 | U06 | U06 2025 OVERHAUL | 2025-09-08 07:00 | 2025-12-03 17:00 | 51.3
ROCK ISLAND #2 | U05 | Required out for U05 Gen-lead replacement and U06 draft tube gate cylinder and HPU refurbishment | 2025-09-08 07:00 | 2025-10-10 17:00 | 51.3
ROCK ISLAND #2 | U03 | U03 2025 REHAB | 2025-11-26 07:00 | 2026-11-23 17:00 | 51.3
ROCK ISLAND #2 | U02 | U02 2026 OVERHAUL | 2026-09-14 07:10 | 2026-11-19 17:50 | 51.3
ROCK ISLAND #2 | U04 | U04 2025 REHAB | 2026-11-02 07:00 | 2027-10-27 17:00 | 51.3
ROCK ISLAND #2 | U01 | 2027 OVH | 2027-09-12 07:10 | 2027-11-12 17:50 | 51.3
ROCK ISLAND #2 | U08 | U08 2026 REHAB | 2027-10-05 07:00 | 2028-09-27 17:00 | 51.3
ROCK ISLAND #2 | U05 | U05 2028 OVERHAUL | 2028-03-01 07:10 | 2028-05-11 17:50 | 51.3
ROCK ISLAND #2 | U06 | U06 2027 REHAB | 2028-09-06 07:00 | 2029-08-31 17:00 | 51.3
ROCK ISLAND #2 | U02 | U02 2028 REHAB | 2029-08-10 07:00 | 2030-08-02 17:00 | 51.3
ROCK ISLAND #2 | U07 | U07 2029 OVERHAUL | 2029-09-11 07:10 | 2029-11-14 17:50 | 51.3